## Sheet1
ID | Cycle | Issue | Reported By | Reported On | Description | Query/ Docs | Resolution | Status | Resolved On
1 | C02 | Meters With No Readings | RCO | 2013-11-20 | Conventional meters in apmedida_ap without any readings in AP_CO and have no apmedida_param | select count(*) from apmedida_ap where (co_marca,num_apa) not in (select co_marca, num_apa from apmedida_co) and tip_apa <>'TA100'; select count(*) from apmedida_ap where (co_marca,num_apa) not in (select co_marca, num_apa from apmedida_param) and tip_apa<>'TA100'; | Created all the necessary readings on converted database. Also this change was done on the code | In Progress
2 | C02 | MT meters without 3 consumptions | RCO | 2013-11-20 | MT meters (TA165) should have 3 consumption types. They are some TA165 meters without the 3. | select num_apa, co_marca, tip_csmo from apmedida_ap ap, csmo_apa cs where ap.tip_apa = cs.tip_apa and exists (select 0 from apmedida_param where nis_rad = ap.nis_rad) minus select num_apa, co_marca, tip_csmo from apmedida_param |  | In Progress
3 | C02 | CLIENTES.DATOS2 | RCO | 2013-11-20 | The default value ‘/1/6/ / / / / / /’ must be in CLIENTES.DATOS, not CLIENTES.DATOS2 |  | Updated CLIENTES.DATOS2 to space Also changed the program | Resolved | 20/.11/2013
4 | C02 | Prepaid reading periodicity | RCO | 2013-11-20 | Reading periodicity for prepaid customers is supposed to be quaterly and not monthly. |  | The affected table was SUMCON and this has been updated and changed on the program. For AP_AP, FPL and RUTAS this was already corrected. | Resolved | 2013-11-20
5 | C02 | Puntomed_Param.F_Val | RCO | 2013-11-20 | The valid from date on puntomed_param should be same or earlier than the meter installation date. | select count(p.nis_rad) from puntomed_param p, apmedida_ap a where a.nis_rad=p.nis_rad and p.f_val>a.f_inst; | Currently this date is coming from the service contracting date. We are investigating why we have some dates for meter installations which are earlier than contracting date. | In Progress