## Sheet1
System | Data Requested | Description | Status | Responsible (Part Affecting) | Due Date | Comments
Cadastramento | Customer Data | A format was provided, this will be used to provide conversion data to conversion team. | Pending | EDM | 2013-11-07 | Some data elements on the received data were not OK and Indra has requested another copy of the extraction.
Eclipse | Static Data Format | A format was provided, this will be used to provide Eclipse data for conversion. | Provided | EDM | 2013-10-31 | Data received OK
Galatee | Billing Format | A format for all the bills in the last 24 months | Provided - Indra to process the extracted data now | EDM | 2013-11-06 | Due to SQLBase limitations this format cannot be done in Galatee and it will be loaded into conversion environment and processed from there. Data received from Galatee and loaded on conversion DB already.
Access | Billing Format | A format for all the bills in the last 24 months | Pending | EDM | 2013-11-06 | No communication from EDM on the status
Eclipse | Billing Format | A format for all the purchase of tokens in the last 24 months | Pending | Indra | 2013-11-07 | EDM preparing sample extraction
Galatee | Deposit Format | A format for all the security deposits and their statuses | Pending | Indra | 2013-11-15 | Format ready and sent to EDM.
Access | Deposit Format | A format for all the security deposits and their statuses | Pending | Indra | 2013-11-15 | We have not received billing formats for Access and this can wait until we finish billing first.
Cadastramento | Network Data | Network structure from LV transformers to the upward feeding | Pending | EDM | 2013-11-13 | EDM to provide data
Manual | Mapping Streets to CSC | There is need to map current Bairros and streets in the Cadastramento to the correct CSC | To be discussed in the meeting | EDM | TBA
Manual | Employee IDs | Employees with accounts to be mapped to HR by ID or NUIT | To be discussed in the meeting | EDM/Indra | TBA
Manual | Reading Itineraries | Depending on the size of current reading books, they may be need to split them into small itineraries and provide the reading dates | To be discussed in the meeting | EDM/Indra | TBA
Manual | Non disconnectable Customers | There will be need to flag some customers as not disconnectable. These will be provided in Excel if data not available in current systems | To be discussed in the meeting | EDM/Indra | TBA
Manual | Stored Meters | The inventory of meters not installed. | To be discussed in the meeting | EDM/Indra | TBA
Galatee | Installment agreements | Capture of all instalment agreements which are being carried out manually. | Pending | EDM | 2013-11-22